## Phase-based
Voice-Controlled Virtual Assistant for PwDs Project Plan Breakdown
Project Managers: Sarwar Ebrahimi & Shafiullah Haidari ¦ Project Duration : 1 Year ¦ Project Budget($): 1 million
Research & Requirment Analysis Phase
Goal: Understand users, define the system, and gather requirements.
Duration : 2 months
Total Budget : $50,000
Staff : 2 Researchers, 1 Project Manager
Item |  | Description | Estimated Cost($) | Category | Staff / Team | Duration | Dependencies | Milestone
Internet & research tools |  | Online research tools & software for gathering info | 5000 | Operations | 2 Researchers | 1 month | None | Initial Research complete
Surveys & interviews |  | Conduct surveys/interviews with target users | 10000 | Human Resources | 1 Project Manager, 2 researchers | 1 month | None | Complete User Feedback
Travel |  | Travel for face-to-face interviews | 8000 | Operations | 1 Project Manager | 1 month | Surveys & interviews comlete | Travel completed
Data Collection Tools |  | Purchase tools for survey analysis | 7000 | Equipment | 2 Researchers | 1 month | None | Tools Acquired
Stipends |  | Compensation for research participants | 10000 | Human Resources | 1 Project Manager | 2 months | Surveys & interviews comlete | Data Collection Complete
Miscellaneous costs |  | Unexpected costs(materials, additional tools) | 10000 | Contingency | 2 Researchers | 2 months | Data Collection Tools Acquired | Final Report Complied
Subtotal |  |  | 50000 |  |  | 2 months
System Design & Planning Phase
Goal: Develop the system architecture and design
Duration : 1.5 months
Total Budget : $100,000
Staff : 1 UI/UX Designer, 2 Architects, 1 Project Manager
Item |  | Description | Estimated Cost($) | Category | Staff / Team | Duration | Dependencies | Milestone
Design Tools |  | Figma, Adobe XD for UI/UX Design | 5000 | Equipment | 1 UI/UX Designer | 1.5 month | None | Design Tool Setup
Prototyping Tools |  | Lucidchart, Sketch for wireframes and prototype | 10000 | Software | 1 UI/UX Designer | 1.5 month | None | Prototypes Created
Team Meetings |  | Regular meetings for planning system architecture | 2000 | Operations | 1 Project Manager | 1.5 month | None | Architecture Defined
Architect Consultation |  | External architect to assist with system design | 20000 | Equipment | 2 Researchers | 1 month | None | Architectural Design Finalized
Design Stipends |  | Payment for external designers(constructors) | 15000 | Human Resources | 1 Project Manager | 1.5 months | None | design Finalized
Miscellaneous costs |  | Unexpected costs related to tools for planning | 3000 | Contingency | 2 Researchers | 1.5 month | Architect Consultation complete | Final Design Approval
Subtotal |  |  | 100000 |  |  | 1.5 months
Prototype Development Phase
Goal: Create a working prototype of the system
Duration : 2.5 months
Total Budget : $150,000
3 Developers, 1 AI/ML Engineer, 1 Project Manager
Item |  | Description | Estimated Cost($) | Category | Staff / Team | Duration | Dependencies | Milestone
Hardware Purchase |  | Raspberry Pi, microphones, sensors, etc. | 20000 | Equipment | 2 Developers | 2.5 month | Design Finalized | Hardware Set Up
Software/API Costs |  | Google Speech-to-Text, Dialogflow APIs | 25000 | Software | 3 Developers | 2.5 month | None | API Integration Complete
Developer Salaries |  | Full-Stack developer costs | 80000 | Human Resources | 3 Developers | 2.5 month | None | Prototype Developed
AI/ML Engineer Salary |  | Salary for AI/ML Engineer working on speech features | 25000 | Human Resources | 1 AI/ML Engineer | 2.5 month | None | Speech Recognition Working
Subtotal |  |  | 50000 |  |  | 2 months
Full Development Phase
Goal: Full system development with integration of all components
Duration : 4 months
Total Budget : $400,000
Staff : 5 Developers, 2 AI Engineers, 1 UI/UX Designer, 1 Project Manager
Item |  | Description | Estimated Cost($) | Category | Staff / Team | Duration | Dependencies | Milestone
Backend Development |  | Development of server-side features, API intergration | 150000 | Human Resources | 3 Developers | 4 months | Prototype Dev complete | Backend Completed
Frontend Development |  | Development of the UI/UX interface | 100000 | Human Resources | 2 Developers | 4 months | Prototype Dev complete | UI/UX Completed
AI/ML Engine |  | Development of AI and Machine Learning algorithms | 50000 | Human Resources | 2 AI Engineers | 4 months | Prototype Dev complete | AI System Finalized
Cloud Services(AWS) |  | Hosting on cloud platforms(AWS, Azure) | 50000 | Software | 0 | 4 months | Backend Dev Complete | System Hosted
Software Licenses |  | Licensing for tools like TensorFlow, Docker, etc. | 20000 | Software | 0 | 4 months | None | Software Tools Available
Miscellaneous costs |  | Unexpected costs(materials, additional tools) | 10000 | Contingency | 2 Researchers | 2 months | Data Collection Tools Acquired | Final Report Complied
Subtotal |  |  | 400000 |  |  | 2 months
Testing & Validation Phase
Goal: Ensure usability, accessibility, and fix bugs.
Duration : 2 months
Total Budget : $100,000
2 Testers, 1 AQ Engineer, 1 Project Manager
Item |  | Description | Estimated Cost($) | Category | Staff / Team | Duration | Dependencies | Milestone
User Testing |  | Field testing with disabled users | 30000 | Operations | 2 Testers | 2 months
Accessibility Testing |  | Specialized tools to assess accessibility | 20000 | Equipment | 1 QA Engineer | 2 months
Bug Fixing |  | Fix bugs | 8000 | Operations | 1 Project Manager | 1 month
Miscellaneous costs |  | Unexpected costs(materials, additional tools) | 10000 | Contingency | 2 Researchers | 2 months
Subtotal |  |  | 50000 |  |  | 2 months
Deployment & Launch Phase
Goal: Finalize deployment and launch the product to users.
Duration : 1 month
Total Budget : $50,000
3 Developers, 1 DevOps Engineer, 1 Project Manager
Item |  | Description | Estimated Cost($) | Category | Staff / Team | Duration | Dependencies | Milestone
Final Hosting Setup |  | Set up production environment(servers, databases) | 10000 | Software | 1 DevOps Engineer | 1 month
App Deployment(Play Store, etc.) |  | Deploy to Play Store, App Store | 5000 | Operations | 2 Developers | 1 month
Documentaion |  | Write system and user documentation | 10000 | Human Resources | 1 Project Manager | 1 month
Domain & Hosting Costs |  | Purchase domain and final hosting services | 15000 | Operations | 1 Developer | 1 month
Marketing |  | Marketing compaign for product launch | 10000 | Operations | 1 Project Manager | 2 months
Subtotal |  |  | 50000 |  |  | 2 months
Maintenance & Support Phase
Goal: Ensure system uptime, monitor for issues, and provide continous updates.
Duration : Ongoing(1 month within the year)
Total Budget : $50,000
Staff : 2 Support Engineers, 1 Developer, 1 Project Manager
Item |  | Description | Estimated Cost($) | Category | Staff / Team | Duration | Dependencies | Milestone
Monthly Cloud Costs |  | Ongoing hosting and cloud service expenses | 15000 | Operations | 1 Project Manager | 1 month
Developer Salaries |  | Support for bug fixes and updates | 20000 | Human Resources | 1 Developer | 1 month
Support Engineer Salaries |  | Staff for technical support | 10000 | Human Resources | 2 Support Engineers | 1 month
Miscellaneous costs |  | Unexpected maintenace costs | 5000 | Contingency | 1 Project Manager | 2 months
Subtotal |  |  | 50000 |  |  | 2 months

## PC-based
Voice-Controlled Virtual Assistant for PwDs Project Plan Breakdown
Project Managers: Sarwar Ebrahimi & Shafiullah Haidari ¦ Project Duration : 1 Year ¦ Project Budget($): 1 million
Research & Requirment Analysis Phase
Goal: Understand users, define the system, and gather requirements.
Duration : 2 months
Total Budget : $64,000 (5%)
Category | Role | Salary |  | No_Staff | Extra_Hour |  | Extra_Salary |  | Duration(month) |  | Total | Percenatage
Human Resources | Project Manager | 3000 |  | 1 | 10 |  | 41.6667 |  | 2 |  | 6041.6667 | 9.44%
| Researcher | 2000 |  | 2 | 12 |  | 33.3333 |  | 2 |  | 8033.3333 | 12.55%
| Driver | 600 |  | 1 | 8 |  | 6.6667 |  | 2 |  | 1206.6667 | 1.885%
| Cook | 500 |  | 1 | 0 |  | 0 |  | 2 |  | 1000 | 1.562%
| Cleaner | 400 |  | 1 | 0 |  | 0 |  | 2 |  | 800 | 1.25%
| Guard | 800 |  | 1 | 0 |  | 0 |  | 2 |  | 1600 | 2.5%
| Subtotal | 7300 |  | 7 | 30 |  | 81.6667 |  |  |  | 18681.6667 | 29.19%
Equipments | Item | Description |  |  | Qunatity | Unit Cost | Total Cost |  | Priority |  | Status | Percentage
| Laptop(Core i5, 16GB RAM) | For research,documentation, and analysis |  |  | 5 | 800 | 4000 |  | High |  | Planned | 6.25%
| Tablets(survey) | Office-base research and storage |  |  | 2 | 600 | 1200 |  | High |  | Planned | 1.875%
| External Hard Drive | Backup of research data and recordings |  |  | 2 | 60 | 120 |  | High |  | Planned | 0.1875%
| Wi-Fi Router | Internect connectivity for team |  |  | 2 | 100 | 200 |  | High |  | Planned | 0.3125%
| LAN Cables | Network Setup |  |  | 5 | 8 | 40 |  | High |  | Planned | 0.0625%
| Audio recorders | For voice data collection |  |  | 2 | 100 | 200 |  | Medium |  | Planned | 0.3125%
| Subtotal |  |  |  | 18 | 1668 | 5760 |  |  |  |  | 9%
Software & Licenses | Name | Purpose |  |  | License Type |  | Quantity |  | Unit Cost |  | Total Cost | Percentage
| Survey Tools | Google Forms Pro for data collection, etc |  |  | Paid |  | 2 |  | 150 |  | 300 | 0.4688%
| MS Office / Google Workspace | Necessary for documentation |  |  | Paid |  | 4 |  | 500 |  | 2000 | 3.125%
| Data Analysis Tools | Necessary for research |  |  | Paid |  | 2 |  | 700 |  | 1400 | 2.188%
| SPSS | Data analysis(quantitive research) |  |  | Licennse(short-term) |  | 2 |  | 300 |  | 600 | 0.9375%
| Subtotal | [5 empty] | 10 |  | 1650 |  | 4300 | 6.719%
Office & Operations | Item | Description |  |  | Qunatity |  | Duration(month) |  | Unit Cost |  | Total Cost | Percentage
| Office Rent | The room rent for office |  |  |  |  | 2 |  | 4000 |  | 8000 | 12.5%
| Electricity | The taxes of electricity of the office |  |  |  |  | 2 |  | 1000 |  | 2000 | 3.125%
| Internet | The internect taxes within a month |  |  |  |  | 2 |  | 1000 |  | 2000 | 3.125%
| Water | The taxes of used water in a month |  |  |  |  | 2 |  | 200 |  | 400 | 0.625%
| Office Furniture | The necessary furniture for office setup |  |  |  |  | 2 |  | 1500 |  | 3000 | 4.688%
| cleaning Services | The cleaning services, garbage collection |  |  |  |  | 2 |  | 600 |  | 1200 | 1.875%
| Stationary | Pen, paper, printer, etc |  |  |  |  | 2 |  | 1000 |  | 2000 | 3.125%
| Subtotal |  |  |  | 0 |  |  |  | 9300 |  | 18600 | 29.06%
Travel & Living Expenses | Item | Description |  |  | Qunatity/Duration |  | Travel Details |  | Cost |  | Total Cost | Percentage
| Field visits Transport | Transport for visiting PwDs(taxi/rented car) |  |  | 20 |  | Kabul + nearby districts |  | 80 |  | 1600 | 2.5%
| Accommodation | rural ares/ Hotel for field team |  |  | 10 |  | mid-level |  | 50 |  | 500 | 0.7812%
| Travel to Provinces | Travel to 2 provinces |  |  | 2 |  | Bamyan/ Herat |  | 600 |  | 1200 | 1.875%
| Feul Cost | Fuel for rented vihecle |  |  | 10 |  | The cost of feul |  | 700 |  | 7000 | 10.94%
| Food & Meals | Daily meals for team |  |  | 60 |  | Field work days |  | 25 |  | 1500 | 2.344%
| Subtotal |  |  |  | 102 |  |  |  | 1455 |  | 11800 | 18.44%
Contingency | Risk Category | Description |  |  | Cost |  |  |  | Total Cost |  | Percentage
| Technical | The technical related taxes |  |  | 4000 |  |  |  | 4000 |  | 6.25%
| Finincial | The financila related taxes |  |  | 4000 |  |  |  | 4000 |  | 6.25%
| Operational | The operation related taxes |  |  | 3500 |  |  |  | 3500 |  | 5.469%
| Legal | The legal cases taxes |  |  | 2500 |  |  |  | 2500 |  | 3.906%
| Subtotal |  |  |  | 14000 |  |  |  | 14000 |  | 21.88%
System Design & Planning Phase
Goal: Develop the system architecture and design
Duration : 1.5 months
Total Budget : $114,000(10%)
Category | Role | Salary(month) |  | No_Staff | Extra_Hour |  | Extra_Salary |  | Duration(month) |  | Total | Percenatage
Human Resources | Project Manager | 3000 |  | 1 | 7 |  | 29.1667 |  | 1.5 |  | 4529.1667 | 3.973%
| UI/UX Designer | 1500 |  | 1 | 8 |  | 16.6667 |  | 1.5 |  | 2266.6667 | 1.988%
| Software Architect | 3000 |  | 2 | 10 |  | 41.6667 |  | 1.5 |  | 9041.6667 | 7.931%
| Cook | 500 |  | 1 | 0 |  | 0 |  | 1.5 |  | 750 | 0.6579%
| Cleaner | 400 |  | 1 | 0 |  | 0 |  | 1.5 |  | 600 | 0.5263%
| Quard | 800 |  | 1 | 0 |  | 0 |  | 1.5 |  | 1200 | 1.053%
| Driver | 600 |  | 1 | 0 |  | 0 |  | 1.5 |  | 900 | 0.7895%
| Subtotal | 9800 |  | 8 | 25 |  | 87.5 |  |  |  | 19287.5 | 16.92%
Equipments | Item |  | Description |  |  |  | Quantity | Unit Cost | Total Cost | Priority | Status | Percentage
| Whiteboard & Markers |  | Drawing System Architecture Diagrams |  |  |  | 2 | 100 | 200 | Meduim | Planned | 0.1754%
| Projector |  | Presenting system design to team |  |  |  | 1 | 500 | 500 | High | Planned | 0.4386%
| External Monitors |  | For better UI/UX & system modeling work |  |  |  | 3 | 200 | 600 | High | Planned | 0.5263%
| UPS(Power backup) |  | Backup during electricity cuts |  |  |  | 2 | 250 | 500 | High | Planned | 0.4386%
| Grahpics tablet |  | Necessary for the UI/UX design |  |  |  | 1 | 300 | 300 | Meduim | Planned | 0.2632%
| Subtotal | [5 empty] | 9 | 1350 | 2100 |  |  | 1.842%
Software & Licenses | Name | Purpose |  |  | License Type |  | Quantity |  | Unit Cost |  | Total Cost | Percentage
| Figma / Adobe XD | For UI/UX design |  |  | Paid / Free |  | 2 |  | 400 |  | 800 | 0.7018%
| Architecture tools | Designing the architecture of the system |  |  | Paid |  | 5 |  | 300 |  | 1500 | 1.316%
| Cloud sandbox | For design of architecture |  |  | Paid |  | 4 |  | 500 |  | 2000 | 1.754%
| Microsoft Office 365 | Documentation,reports,Excel Analysis |  |  | Paid/ Free |  | 2 |  | 250 |  | 500 | 0.4386%
| DB modeling tools | tools for modeling dababase |  |  | Paid |  | 6 |  | 400 |  | 2400 | 2.105%
| Diagram tools | Lucidchart, Draw.io |  |  | Paid |  | 4 |  | 200 |  | 800 | 0.7018%
| Accessibilty design | Tools for the design of accessibilty |  |  | Paid |  | 4 |  | 300 |  | 1200 | 1.053%
| Subtotal | [5 empty] | 27 |  | 2350 |  | 9200 | 8.07%
Office & Operations | Item | Description |  |  | Qunatity |  | Duration(month) |  | Unit Cost |  | Total Cost | Percentage
| Office Rent | The room rent for office |  |  |  |  | 1.5 |  | 800 |  | 1200 | 1.053%
| Electricity | The taxes of electricity of the office |  |  |  |  | 1.5 |  | 300 |  | 450 | 0.3947%
| Internet | The internect taxes within a month |  |  |  |  | 1.5 |  | 400 |  | 600 | 0.5263%
| Water | The taxes of used water in a month |  |  |  |  | 1.5 |  | 200 |  | 300 | 0.2632%
| Office Furniture | The necessary furniture for office setup |  |  |  |  | 1.5 |  | 700 |  | 1050 | 0.9211%
| cleaning Services | The cleaning services, garbage collection |  |  |  |  | 1.5 |  | 100 |  | 150 | 0.1316%
| Stationary | Pen, paper, printer, etc |  |  |  |  | 1.5 |  | 500 |  | 750 | 0.6579%
| Security Services | The necessary tools related to security |  |  |  |  | 1.5 |  | 400 |  | 600 | 0.5263%
| Subtotal | [7 empty] | 3400 |  | 5100 | 4.474%
Travel & Living Expenses | Item |  | Description |  |  | Quantity | Travel Details |  | Cost |  | Total Cost | Percentage
| Stakeholder workshop |  | The workshop between stakehoders |  |  | 2 |  |  | 400 |  | 800 | 0.7018%
| Accommlodation |  | The living/accommodation costs |  |  | 1 |  |  | 600 |  | 600 | 0.5263%
| Daily allowance |  | small stipends of the teams |  |  | 1 |  |  | 700 |  | 700 | 0.614%
| Field visits to PwDs centers |  | To design the system based on requirments |  |  | 1 |  |  | 800 |  | 800 | 0.7018%
[11 empty] | 0 | 0%
| Subtotal |  |  |  |  | 5 |  |  | 2500 |  | 2900 | 2.544%
Contingency | Risk Category | Description |  |  | Cost |  |  |  | Total Cost |  | Percentage
| Technical |  |  |  | 4000 |  |  |  | 4000 |  | 3.509%
| Finincial |  |  |  | 4000 |  |  |  | 4000 |  | 3.509%
| Operational |  |  |  | 3500 |  |  |  | 3500 |  | 3.07%
| Legal |  |  |  | 2500 |  |  |  | 2500 |  | 2.193%
| Subtotal |  |  |  | 14000 |  |  |  | 14000 |  | 12.28%
Prototype Development Phase
Goal: Create a working prototype of the system
Duration : 2.5 months
Total Budget : $164,000(15%)
Category | Role | Salary(month) |  | No_Staff | Extra_Hour |  | Extra_Salary |  | Duration(month) |  | Total | Percenatage
Human Resources | Project Manager | 3000 |  | 1 | 10 |  | 41.6667 |  | 2.5 |  | 7541.6667 | 4.599%
| Full-Stack Developer | 2500 |  | 3 | 15 |  | 52.0833 |  | 2.5 |  | 18802.0833 | 11.46%
| AI/ML Engineer | 3000 |  | 1 | 12 |  | 50 |  | 2.5 |  | 7550 | 4.604%
| Cook | 500 |  | 1 | 0 |  | 0 |  | 2.5 |  | 1250 | 0.7622%
| Cleaner | 400 |  | 1 | 0 |  | 0 |  | 2.5 |  | 1000 | 0.6098%
| Quard | 800 |  | 1 | 0 |  | 0 |  | 2.5 |  | 2000 | 1.22%
| Driver | 600 |  | 1 | 0 |  | 0 |  | 2.5 |  | 1500 | 0.9146%
| Subtotal | 10800 |  | 9 | 37 |  | 143.75 |  |  |  | 39643.75 | 24.17%
Equipments | Item | Description |  |  | Qunatity | Unit Cost | Total Cost |  | Priority |  | Status | Percentage
Dev machines
Testing phones/devices
Servers
Subtotal
Software & Licenses | Name | Purpose |  |  | License Type |  | Unit Cost |  | Total Cost |  | Percentage
| APIs | speech recognition
Dev tools
cluoud usage
Subtotal
Office & Operations | Item | Description |  |  | Qunatity |  | Duration(month) |  | Unit Cost |  | Total Cost | Percentage
| Office Rent | The room rent for office |  |  |  |  | 2.5 |  | 800 |  | 2000 | 1.22%
| Electricity | The taxes of electricity of the office |  |  |  |  | 2.5 |  | 300 |  | 750 | 0.4573%
| Internet | The internect taxes within a month |  |  |  |  | 2.5 |  | 400 |  | 1000 | 0.6098%
| Water | The taxes of used water in a month |  |  |  |  | 2.5 |  | 200 |  | 500 | 0.3049%
| Office Furniture | The necessary furniture for office setup |  |  |  |  | 2.5 |  | 700 |  | 1750 | 1.067%
| cleaning Services | The cleaning services, garbage collection |  |  |  |  | 2.5 |  | 100 |  | 250 | 0.1524%
| Stationary | Pen, paper, printer, etc |  |  |  |  | 2.5 |  | 500 |  | 1250 | 0.7622%
| Security Services | The necessary tools related to security |  |  |  |  | 2.5 |  | 400 |  | 1000 | 0.6098%
| Subtotal | [7 empty] | 3400 |  | 8500 | 5.183%
Travel & Living Expenses | Item | Description |  |  | Qunatity |  | Travel Details |  | Cost |  | Total Cost | Percentage
Subtotal
Contingency | Risk Category | Description |  |  | Cost |  |  |  | Total Cost |  | Percentage
| Technical |  |  |  | 4000 |  |  |  | 4000 |  | 2.439%
| Financial |  |  |  | 4000 |  |  |  | 4000 |  | 2.439%
| Operational |  |  |  | 3500 |  |  |  | 3500 |  | 2.134%
| Legal |  |  |  | 2500 |  |  |  | 2500 |  | 1.524%
| Subtotal |  |  |  | 14000 |  |  |  | 14000 |  | 8.537%
Full Development Phase
Goal: Full system development with integration of all components
Duration : 4 months
Total Budget : $414,000(40%)
Category | Role | Salary(month) |  | No_Staff | Extra_Hour |  | Extra_Salary |  | Duration(month) |  | Total | Percenatage
Human Resources | Project Manager | 3000 |  | 1 | 10 |  | 41.6667 |  | 4 |  | 12041.6667 | 2.909%
| UI/UX Designer | 1500 |  | 1 | 8 |  | 16.6667 |  | 4 |  | 6016.6667 | 1.453%
| Full-Stack Developer | 2500 |  | 5 | 15 |  | 52.0833 |  | 4 |  | 50052.0833 | 12.09%
| AI/ML Engineer | 3000 |  | 2 | 10 |  | 41.6667 |  | 4 |  | 24041.6667 | 5.807%
| Cleaner | 400 |  | 1 | 0 |  | 0 |  | 4 |  | 1600 | 0.3865%
| Quard | 800 |  | 1 | 0 |  | 0 |  | 4 |  | 3200 | 0.7729%
| Cook | 500 |  | 1 | 0 |  | 0 |  | 4 |  | 2000 | 0.4831%
| Driver | 600 |  | 1 | 0 |  | 0 |  | 4 |  | 2400 | 0.5797%
| Subtotal | 12300 |  | 13 | 43 |  | 152.0833 |  |  |  | 101352.0833 | 24.48%
Equipments | Item |  | Description |  |  | Quantity | Unit Cost | Total Cost | Priority |  | Status | Percentage
| Laptops |  | High performance for develpoers |  |  | 4 | 800 | 3200 | High |  | Planned | 0.7729%
| Dedicated GPU machine |  | For AI training |  |  | 8 | 1000 | 8000 | High |  | Planned | 1.932%
| Local server |  | For having services locally |  |  | 2 | 1200 | 2400 | Medium |  | Planned | 0.5797%
| cooling systems |  | imprtant for hardware |  |  | 10 | 500 | 5000 | Medium |  | Planned | 1.208%
| cable management tools |  | For building the internal system |  |  | 4 | 300 | 1200 | Medium |  | Planned | 0.2899%
| External GPU |  | Optional |  |  | 2 | 900 | 1800 | Low |  | Planned | 0.4348%
| Backup UPS System |  | For electricity power backup |  |  | 1 | 300 | 300 | Medium |  | Planned | 0.07246%
| Subtotal |  |  |  |  | 31 | 5000 | 21900 |  |  |  | 5.29%
Software & Licenses | Name |  | Purpose |  |  |  | License Type |  | Quantity | Unit Cost | Total Cost | Percentage
| IDEs |  | VS Code, IntelliJ, PyCharm Pro |  |  |  | Paid |  | 4 | 600 | 2400 | 0.5797%
| Cloud compute |  | AWS EC2, Azure VM |  |  |  | Paid |  | 4 | 800 | 3200 | 0.7729%
| Storage Services |  | S3, Blob storage |  |  |  | Paid |  | 3 | 700 | 2100 | 0.5072%
| Speech APIs |  | Google Speech-to-Text, Azure Speech |  |  |  | Paid |  | 6 | 1000 | 6000 | 1.449%
| NLP tools |  | OpenAI API, HuggingFace |  |  |  | Paid |  | 4 | 800 | 3200 | 0.7729%
| DB licenses |  | Some may need licenses |  |  |  | Paid / Free |  | 4 | 500 | 2000 | 0.4831%
| API testing tools |  | Postman |  |  |  | Paid |  | 2 | 400 | 800 | 0.1932%
| Security tools |  | code scanning tools |  |  |  | Paid |  | 2 | 900 | 1800 | 0.4348%
| Container tools |  | Docker |  |  |  | Paid |  | 6 | 1000 | 6000 | 1.449%
| CI/CD tools |  | GitHub Actions, Jenkins |  |  |  | Paid |  | 4 | 750 | 3000 | 0.7246%
| Subtotal | [7 empty] | 39 | 7450 | 30500 | 7.367%
Office & Operations | Item | Description |  |  | Qunatity |  | Duration(month) |  | Unit Cost |  | Total Cost | Percentage
| Office Rent | The room rent for office |  |  |  |  | 4 |  | 800 |  | 3200 | 0.7729%
| Electricity | The taxes of electricity of the office |  |  |  |  | 4 |  | 300 |  | 1200 | 0.2899%
| Internet | The internect taxes within a month |  |  |  |  | 4 |  | 400 |  | 1600 | 0.3865%
| Water | The taxes of used water in a month |  |  |  |  | 4 |  | 200 |  | 800 | 0.1932%
| Office Furniture | The necessary furniture for office setup |  |  |  |  | 4 |  | 700 |  | 2800 | 0.6763%
| cleaning Services | The cleaning services, garbage collection |  |  |  |  | 4 |  | 100 |  | 400 | 0.09662%
| Stationary | Pen, paper, printer, etc |  |  |  |  | 4 |  | 500 |  | 2000 | 0.4831%
| Security Services | The necessary tools related to security |  |  |  |  | 4 |  | 400 |  | 1600 | 0.3865%
| Subtotal | [7 empty] | 3400 |  | 13600 | 3.285%
Travel & Living Expenses | Item |  | Description |  |  | Quantity | Travel Details |  | Cost |  | Total Cost | Percentage
Developer meetings
| Remote work support |  | for data packages
Internal workshops
Team collaboration events
Subtotal
Contingency | Risk Category | Description |  |  | Cost |  |  |  | Total Cost |  | Percentage
| Technical |  |  |  | 4000 |  |  |  | 4000 |  | 0.9662%
| Financial |  |  |  | 4000 |  |  |  | 4000 |  | 0.9662%
| Operational |  |  |  | 3500 |  |  |  | 3500 |  | 0.8454%
| Legal |  |  |  | 2500 |  |  |  | 2500 |  | 0.6039%
| Subtotal |  |  |  | 14000 |  |  |  | 14000 |  | 3.382%
Testing & Validation Phase
Goal: Ensure usability, accessibility, and fix bugs.
Duration : 2 months
Total Budget : $114,000(10%)
Category | Role | Salary(month) |  | No_Staff | Extra_Hour |  | Extra_Salary |  | Duration(month) |  | Total | Percenatage
Human Resources | Project Manager | 3000 |  | 1 | 10 |  | 41.6667 |  | 2 |  | 6041.6667 | 5.3%
| Tester | 1200 |  | 2 | 12 |  | 20 |  | 2 |  | 4820 | 4.228%
| QA Engineer | 1600 |  | 1 | 10 |  | 22.2222 |  | 2 |  | 3222.2222 | 2.827%
| Cook | 500 |  | 1 | 0 |  | 0 |  | 2 |  | 1000 | 0.8772%
| Cleaner | 400 |  | 1 | 0 |  | 0 |  | 2 |  | 800 | 0.7018%
| Quard | 800 |  | 1 | 0 |  | 0 |  | 2 |  | 1600 | 1.404%
| Driver | 600 |  | 1 | 0 |  | 0 |  | 2 |  | 1200 | 1.053%
| Subtotal | 8100 |  | 8 | 32 |  | 83.8889 |  |  |  | 18683.8889 | 16.39%
Equipments | Item |  | Quantity |  |  | Quantity | Unit Cost | Total Cost | Priority |  | Status | Percentage
| Smartphones |  | multiple low-end and high-end
| Assistive devices |  | Screen readers, braille tools if possible
| Noise testing equipment |  | The tools for testing the noise
| Audio calibration tools |  | Adjusting the related tones
| Recording devices |  | for feedback
Subtotal
Software & Licenses | Name |  | Purpose |  |  |  | License Type |  | Unit Cost |  | Total Cost | Percentage
| Automation tools |  | Selenium, Cypress
| Performance tools |  | Jmeter, LoadRunner
| Bug tracking |  | Jira, Bugzilla
| Accessibility testing tools |  | WAVE, Axe
Device emulators
Voice testing software
Log monitoring tools
Subtotal
Office & Operations | Item | Description |  |  | Qunatity |  | Duration(month) |  | Unit Cost |  | Total Cost | Percentage
Office Rent
Electricity
Internet
Water
Office Furniture
cleaning Services
Stationary
Security Services
Subtotal
Travel & Living Expenses | Item |  | Description |  |  | Quantity | Travel Details |  | Cost |  | Total Cost | Percentage
Travel to user testing locations
| Accommodation |  | The accommodation of the testing teams
Food & daily allowance
| PwDs user participation |  | The user participation incentives
Subtotal
Contingency | Risk Category | Description |  |  | Cost |  |  |  | Total Cost |  | Percentage
| Technical |  |  |  | 4000 |  |  |  | 4000 |  | 3.509%
| Financial |  |  |  | 4000 |  |  |  | 4000 |  | 3.509%
| Operational |  |  |  | 3500 |  |  |  | 3500 |  | 3.07%
| Legal |  |  |  | 2500 |  |  |  | 2500 |  | 2.193%
| Subtotal |  |  |  | 14000 |  |  |  | 14000 |  | 12.28%
Deployment & Launch Phase
Goal: Finalize deployment and launch the product to users.
Duration : 1 month
Total Budget : $64,000(5%)
Category | Role | Salary(month) |  | No_Staff | Extra_Hour |  | Extra_Salary |  | Duration(month) |  | Total | Percenatage
Human Resources | Project Manager | 3000 |  | 1 | 10 |  | 41.6667 |  | 1 |  | 3041.6667 | 4.753%
| Full-Stack Developer | 2500 |  | 3 | 3 |  | 10.4167 |  | 1 |  | 7510.4167 | 11.74%
| DevOps Engineer | 3000 |  | 1 | 12 |  | 50 |  | 1 |  | 3050 | 4.766%
| Cook | 500 |  | 1 | 0 |  | 0 |  | 1 |  | 500 | 0.7812%
| Cleaner | 400 |  | 1 | 0 |  | 0 |  | 1 |  | 400 | 0.625%
| Quard | 800 |  | 1 | 0 |  | 0 |  | 1 |  | 800 | 1.25%
| Driver | 600 |  | 1 | 0 |  | 0 |  | 1 |  | 600 | 0.9375%
| Subtotal | 10800 |  | 9 | 25 |  | 102.0833 |  |  |  | 15902.0833 | 24.85%
Equipments | Item | Description |  | Quantity | Unit Cost |  | Total Cost |  | Priority |  | Status | Percentage
Marketing tools
Installation kits
Load balancer dev
Backup servers
| Production servers | Cloud or physical
Subtotal
Software & Licenses | Name |  |  | Purpose |  |  |  | License Type |  | Unit Cost | Total Cost | Perecentage
| Cloud hosting(AWS, Azure, GCP) |  |  | Set up production environment(servers, databases)
| Domain registration |  |  | Purchase domain and final hosting services
Security Softare(firewall, antivirus)
CDN Services
Backup software
Logging Systems
SSL certificates
Subtotal
Office & Operations | Item | Description |  |  | Qunatity |  | Duration(month) |  | Unit Cost |  | Total Cost | Percentage
Office Rent
Electricity
Internet
Water
Office Furniture
cleaning Services
Stationary
Marketing
Subtotal
Travel & Living Expenses | Item |  | Description |  |  | Quantiy | Travel Details |  | Cost |  | Total Cost | Percentage
Deployment team travel
On-site installation visits
User training sessions
Training accommodation
Transportation of equipment
Accommodations
Foods & meals
Allowance
Subtotal
Contingency | Risk Category | Description |  |  | Cost |  |  |  | Total Cost |  | Percentage
| Technical |  |  |  | 4000 |  |  |  | 4000 |  | 6.25%
| Financial |  |  |  | 4000 |  |  |  | 4000 |  | 6.25%
| Operationl |  |  |  | 3500 |  |  |  | 3500 |  | 5.469%
| Legal |  |  |  | 2500 |  |  |  | 2500 |  | 3.906%
| Subtotal |  |  |  | 14000 |  |  |  | 14000 |  | 21.88%
Maintenance & Support Phase
Goal: Ensure system uptime, monitor for issues, and provide continous updates.
Duration : Ongoing(1 month within the year)
Total Budget : $64,000(5%)
Category | Role | Salary(month) |  | No_Staff | Extra_Hour |  | Extra_Salary |  | Duration(month) |  | Total | Percenatage
Human Resources | Project Manager | 3000 |  | 1 | 10 |  | 41.6667 |  | 1 |  | 3041.6667 | 4.753%
| Support Engineer | 1000 |  | 2 | 8 |  | 11.1111 |  | 1 |  | 2011.1111 | 3.142%
| Full-Stack Developer | 2500 |  | 1 | 5 |  | 17.3611 |  | 1 |  | 2517.3611 | 3.933%
| Cook | 500 |  | 1 | 0 |  | 0 |  | 1 |  | 500 | 0.7812%
| Cleaner | 400 |  | 1 | 0 |  | 0 |  | 1 |  | 400 | 0.625%
| Quard | 800 |  | 1 | 0 |  | 0 |  | 1 |  | 800 | 1.25%
| Driver | 600 |  | 1 | 0 |  | 0 |  | 1 |  | 600 | 0.9375%
| Subtotal | 8800 |  | 8 | 23 |  | 70.1389 |  |  |  | 9870.1389 | 15.42%
Equipments | Item |  | Description |  | Qunatity | Unit Cost | Total Cost |  | Priority |  | Status | Percentage
Support laptops
Monitoring screens
Backup storage system
Network diagnostic tools
Subtotal
Software & Licenses | Name | Purpose |  |  | License Type |  | Unit Cost |  | Total Cost |  | Percentage
| Helpdesk software | Zendesk, Freshdesk
| Monitoring tools | Nagios, Grafana
Security Update tools
CRM tools
Backup & Recovery
Subtotal
Office & Operations | Item | Description |  |  | Qunatity |  | Duration(month) |  | Unit Cost |  | Total Cost | Percentage
Office Rent
Electricity
Internet
Water
Office Furniture
cleaning Services
Stationary
Security Services
Subtotal
Travel & Living Expenses | Item | Description |  |  | Qunatity |  | Travel Details |  | Cost |  | Total Cost | Percentage
Support team travel
Emergency visits
Maintenance trip
Food & Meal
Accommodation
Subtotal
Contingency | Risk Category | Description |  |  | Cost |  |  |  | Total Cost |  | Percentage
| Technical |  |  |  | 4000 |  |  |  | 4000 |  | 6.25%
| Financial |  |  |  | 4000 |  |  |  | 4000 |  | 6.25%
| Operational |  |  |  | 3500 |  |  |  | 3500 |  | 5.469%
| Legal |  |  |  | 2500 |  |  |  | 2500 |  | 3.906%
| Subtotal |  |  |  | 14000 |  |  |  | 14000 |  | 21.88%